## Sheet1
Tasks\Members | Eric | Gwyneth | Adrian | Yu Chen | Yutian | James
Mechanical Design
Documentation | 3 | 3 |  |  | 4 | 4
Software - Odometer/Correction | [5 empty] | 0.5
Software - Obstacle Avoidance
Software - Navigation
Software - Localization
Software - Sensor Filter | [5 empty] | 1
Software - Code Compilation
Hardware - Launching
PowerPoint Presentation |  | 0.5 |  |  |  | 0.5
Integration testing | 3 | 0.5 | 6 | 3 | 3 | 2
LDD sketch design
Meeting with Team + Discussion | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Poster Project |  | 2
Hours Total: | 6.5 | 4.5 | 6.5 | 3.5 | 7.5 | 8.5
Team Members | Primary Role | Week 1 hours | Week 2 & Reading Week hours |  | Week 3 hours | Week 4 hours | Week 5 hours | Week 6 hours | Week 7 hours | Total hours on project | Average Hours
|  | 16 Feb-22 Feb | 23 Feb-8 Mar |  | 9 Mar-15 Mar | 16 Mar-22 Mar | 23 Mar-29 Mar | 30 Mar-5 Apr | 6 Apr-12 Apr
Eric | Proj Man/Software | 5.6 | 0 | 10.5 | 10.7 | 12.7 | 11.9 | 5 | 6.5 | 62.9
Gwyneth | Documents Manager | 5.4 | 0 | 10 | 9 | 10 | 8 | 7.5 | 4.5 | 54.4
Adrian | Software Manager | 4.5 | 0 | 7 | 11 | 15.7 | 13 | 4.5 | 6.5 | 62.2
Yu Chen | Hardware Manager | 5 | 0 | 7 | 8 | 13.5 | 12.5 | 12 | 3.5 | 61.5
Yuting | Hardware | 4.5 | 0 | 7 | 7.5 | 9 | 8.5 | 9 | 7.5 | 53
James | Software | 4.7 | 0 | 8 | 7 | 6.5 | 9 | 9 | 8.5 | 52.7
0
Weekly totals |  | 29.7 | 0 | 49.5 | 53.2 | 67.4 | 62.9 | 47 | 37 | 346.7 | 57.7833