## Time Sheet
Tasks\Members | Eric | Gwyneth | Adrian | Yu Chen | Yuting | James
Mechanical Design | 3 (March 4) | 3 (March 4) | 1 (March 4) | 3 (March 4) | 3 (March 4) | 3 (March 4)
Documentation | 3 (March 5,6) | 3 (March 6,7) | 3 |  |  | 2(March 7)
Software - Odometer | 0 | 0 | 0.5 |  |  | 1(March 7)
Software - Obstacle Avoidance | 1 (March 6) | 0 | 0.5 |  |  | 0
Software - Navigation | 1 (March 6) | 0 | 0.5 |  |  | 0
Software - Localization |  | 0 | 0.5 |  |  | 0
PowerPoint Presentation | 0.5 (March 7) | 2 (March 6) |  |  |  | 0
LDD sketch design |  | 0 |  | 4 (March 6) |  | 0
Meeting with Team + Discussion | 2 (March 4) | 2 (March 4) | 1 (March 4) | 2 (March 4) | 2 (March 4) | 2 (March 4)
Hours Total: | 10.5 | 10 | 7 | 7 | 5 | 8
Team Members | Primary Role | Week 1 hours | Week 2 & Reading Week hours |  | Week 3 hours | Week 4 hours | Week 5 hours | Week 6 hours | Week 7 hours | Total hours on project
|  | 16 Feb-22 Feb | 23 Feb-8 Mar |  | 9 Mar-15 Mar | 16 Mar-22 Mar | 23 Mar-29 Mar | 30 Mar-5 Apr | 6 Apr-12 Apr
Eric | Proj Man/Software | 5.6 |  | 10.5 | [5 empty] | 16.1
Gwyneth | Documents Manager | 5.4 |  | 10 | [5 empty] | 15.4
Adrian | Software Manager | 4.5 |  | 7 | [5 empty] | 11.5
Yu Chen | Hardware Manager | 5 | 0 | 7 | [5 empty] | 12
Yuting | Hardware | 4.5 |  | 5 | [5 empty] | 9.5
James | Software | 4.7 |  | 8 | [5 empty] | 12.7
Weekly totals |  | 29.7 | 0 | 47.5 | 0 | 0 | 0 | 0 | 0 | 77.2