## Time Sheet
Tasks\Members | Eric | Gwyneth | Adrian | Yu Chen | Yutian | James
Mechanical Design | 0 |  |  | 3 | 2
Documentation | 3 | 6 |  | 4 | 4 | 6
Software - Odometer/Correction | 0.5
Software - Obstacle Avoidance | 0.5
Software - Navigation
Software - Localization |  |  | 3
Software - Sensor Filter
Software - Code Compilation |  |  | 0.5
Hardware - Launching |  |  |  | 3
PowerPoint Presentation
Integration testing |  | 0.5 | 1 | 2 | 2 | 2
LDD sketch design
Meeting with Team + Discussion | 1 | 1 |  |  | 1 | 1
Hours Total: | 5 | 7.5 | 4.5 | 12 | 9 | 9
Team Members | Primary Role | Week 1 hours | Week 2 & Reading Week hours |  | Week 3 hours | Week 4 hours | Week 5 hours | Week 6 hours | Week 7 hours | Total hours on project | Average Hours
|  | 16 Feb-22 Feb | 23 Feb-8 Mar |  | 9 Mar-15 Mar | 16 Mar-22 Mar | 23 Mar-29 Mar | 30 Mar-5 Apr | 6 Apr-12 Apr
Eric | Proj Man/Software | 5.6 | 0 | 10.5 | 10.7 | 12.7 | 11.9 | 5 |  | 56.4
Gwyneth | Documents Manager | 5.4 | 0 | 10 | 9 | 10 | 8 | 7.5 |  | 49.9
Adrian | Software Manager | 4.5 | 0 | 7 | 11 | 15.7 | 13 | 4.5 |  | 55.7
Yu Chen | Hardware Manager | 5 | 0 | 7 | 8 | 13.5 | 12.5 | 12 |  | 58
Yuting | Hardware | 4.5 | 0 | 7 | 7.5 | 9 | 8.5 | 9 |  | 45.5
James | Software | 4.7 | 0 | 8 | 7 | 6.5 | 9 | 9 |  | 44.2
0
Weekly totals |  | 29.7 | 0 | 49.5 | 53.2 | 67.4 | 62.9 | 47 | 0 | 309.7 | 51.6167